## Summary
FINANCIAL SUMMARY
Project Title: | Chevron Aerial Drone
Project No : | -
Contract: | -
Manager | Angus Steele
Date: | 2015-02-10
Contribution: | 1.6
|  | Allocated |  |  | Planned |  |  |  | Ratios
|  | Revenue | Planned | Planned | Contrib | Project | Delta to | Running | Running | Contrib | Contrib
Workpackage | Work Package Description | ( R ) | Labour [R] | Running [R] | [R] | Total ( R ) | Allocated [R] | [1] | [2] | [3] | [4]
Phase 1 | Proof of Technical Concept |  | 264840 | 5 | 423744 | 688589 | -688589 |  | 0.00072612 | 159.997
Phase 2 | Development and optimisation against the intended application |  | 529680 | 5 | 847488 | 1377173 | -1377173 |  | 0.00036306 | 159.9985
Phase 3 | Prototype construction and laboratory testing |  | 264840 | 5 | 423744 | 688589 | -688589 |  | 0.00072612 | 159.997
| Totals | 0 | 1059360 | 15 | 1694976 | 2754351 | -2754351 |  | 0.00054459 | 159.9977
[1] Running Ratio = (Running / Revenue) *100
[2] Running Ratio = (Running / Project Total) *100
[3] Contribution Ratio = ( Contribution / ( HR+Running )) * 100
[4] Contribution Ratio = ( Contribution / Revenue) * 100

## WP_1
Project Title: | Chevron Aerial Drone
Project Number: | -
Contract: | -
Author: | Angus Steele
Date: | 2015-02-10
Financial Summary WP 1 |  | Staff Summary
|  |  | Person |  | Staff | Labour | Total | Labour
Description | Value | Name | Index |  | Number | Rate | Hours | Cost
Total Hours: | 1048 | Bosscha P.A | 2 |  | 237958 | 525 | 96 | 50400
Total Labour (R): | 264840 | Steele AW | 39 |  | 303884 | 120 | 480 | 57600
Total Running (R): | 5 | Dickens J.S | 9 |  | 304032 | 195 | 192 | 37440
Contribution (R): | 423744 | Naicker D.M | 27 |  | 250555 | 510 | 160 | 81600
Grand Total (R): | 688589 | Naidoo T. | 28 |  | 235705 | 315 | 120 | 37800
1
1
1
1
1
1
1
Project Planning: | [7 empty] | Plan
|  |  | Person | Task | Staff | Labour | Labour | Running | Labour | Running | Task
Task No. | Description | Person | Index | No. | Number | Hours | Rand |  | Total | Total | Total
1 | Project Management |  | 2 | 1 | 237958 | 96 | 50400 | 1 | 50400 | 1 | 50401
2 | Platform Design |  | 39 | 2 | 303884 | 480 | 57600 | 1 | 57600 | 1 | 57601
3 | Explosion Proofing |  | 9 | 3 | 304032 | 192 | 37440 | 1 | 37440 | 1 | 37441
4 | Radio Communications |  | 27 | 4 | 250555 | 160 | 81600 | 1 | 81600 | 1 | 81601
5 | Camera Work |  | 28 | 5 | 235705 | 120 | 37800 | 1 | 37800 | 1 | 37801
|  |  | 1 | 5
|  |  | 1 | 5
|  |  | 1 | 5
|  |  | 1 | 5
|  |  | 1 | 5
|  |  | 1 | 5
|  |  | 1 | 5
|  |  | 1 | 5
|  |  | 1 | 5
|  |  | 1 | 5
|  |  | 1 | 5
|  |  | 1 | 5
|  |  | 1 | 5
|  |  | 1 | 5
|  |  | 1 | 5
|  |  | 1 | 5
|  |  | 1 | 5
|  |  | 1 | 5
|  |  | 1 | 5
|  |  | 1 | 5
|  |  | 1 | 5
|  |  | 1 | 5
|  |  | 1 | 5
|  |  | 1 | 5
|  |  | 1 | 5
|  |  | 1 | 5
|  |  | 1 | 5
|  |  | 1 | 5
|  |  | 1 | 5
|  |  | 1 | 5
|  |  | 1 | 5
|  |  | 1 | 5
|  |  | 1 | 5
|  |  | 1 | 5
|  |  | 1 | 5
|  |  | 1 | 5
|  |  | 1 | 5
|  |  | 1 | 5
|  |  | 1 | 5
|  |  | 1 | 5
Totals: | [5 empty] | 1048 |  |  | 264840 | 5 | 264845
Note on I39: User @: Fortran Compiler

## WP_2
Project Title: | Chevron Aerial Drone
Project Number: | -
Contract: | -
Author: | Angus Steele
Date: | 2015-02-10
Financial Summary WP2 |  | Staff Summary
|  |  | Person |  | Staff | Labour | Total | Labour
Description | Value | Name | Index |  | Number | Rate | Hours | Cost
Total Hours: | 2096 | Bosscha P.A | 2 |  | 237958 | 525 | 192 | 100800
Total Labour (R): | 529680 | Steele AW | 39 |  | 303884 | 120 | 960 | 115200
Total Running (R): | 5 | Dickens J.S | 9 |  | 304032 | 195 | 384 | 74880
Contribution (R): | 847488 | Naicker D.M | 27 |  | 250555 | 510 | 320 | 163200
Grand Total (R): | 1377173 | Naidoo T. | 28 |  | 235705 | 315 | 240 | 75600
1
1
1
1
1
1
1
Project Planning: | [7 empty] | Plan
|  |  | Person | Task | Staff | Labour | Labour | Running | Labour | Running | Task
Task No. | Description | Person | Index | No. | Number | Hours | Rand |  | Total | Total | Total
1 | Project Management |  | 2 | 1 | 237958 | 192 | 100800 | 1 | 100800 | 1 | 100801
2 | Platform Design |  | 39 | 2 | 303884 | 960 | 115200 | 1 | 115200 | 1 | 115201
3 | Explosion Proofing |  | 9 | 3 | 304032 | 384 | 74880 | 1 | 74880 | 1 | 74881
4 | Radio Communications |  | 27 | 4 | 250555 | 320 | 163200 | 1 | 163200 | 1 | 163201
5 | Camera Work |  | 28 | 5 | 235705 | 240 | 75600 | 1 | 75600 | 1 | 75601
|  |  | 1 | 5
|  |  | 1 | 5
|  |  | 1 | 5
|  |  | 1 | 5
|  |  | 1 | 5
|  |  | 1 | 5
|  |  | 1 | 5
|  |  | 1 | 5
|  |  | 1 | 5
|  |  | 1 | 5
|  |  | 1 | 5
|  |  | 1 | 5
|  |  | 1 | 5
|  |  | 1 | 5
|  |  | 1 | 5
|  |  | 1 | 5
|  |  | 1 | 5
|  |  | 1 | 5
|  |  | 1 | 5
|  |  | 1 | 5
|  |  | 1 | 5
|  |  | 1 | 5
|  |  | 1 | 5
|  |  | 1 | 5
|  |  | 1 | 5
|  |  | 1 | 5
|  |  | 1 | 5
|  |  | 1 | 5
|  |  | 1 | 5
|  |  | 1 | 5
|  |  | 1 | 5
|  |  | 1 | 5
|  |  | 1 | 5
|  |  | 1 | 5
|  |  | 1 | 5
|  |  | 1 | 5
|  |  | 1 | 5
|  |  | 1 | 5
|  |  | 1 | 5
|  |  | 1 | 5
Totals: | [5 empty] | 2096 |  |  | 529680 | 5 | 529685

## WP_3
Project Title: | Chevron Aerial Drone
Project Number: | -
Contract: | -
Author: | Angus Steele
Date: | 2015-02-10
Financial Summary WP3 |  | Staff Summary
|  |  | Person |  | Staff | Labour | Total | Labour
Description | Value | Name | Index |  | Number | Rate | Hours | Cost
Total Hours: | 1048 | Bosscha P.A | 2 |  | 237958 | 525 | 96 | 50400
Total Labour (R): | 264840 | Steele AW | 39 |  | 303884 | 120 | 480 | 57600
Total Running (R): | 5 | Dickens J.S | 9 |  | 304032 | 195 | 192 | 37440
Contribution (R): | 423744 | Naicker D.M | 27 |  | 250555 | 510 | 160 | 81600
Grand Total (R): | 688589 | Naidoo T. | 28 |  | 235705 | 315 | 120 | 37800
1
1
1
1
1
1
1
Project Planning: | [7 empty] | Plan
|  |  | Person | Task | Staff | Labour | Labour | Running | Labour | Running | Task
Task No. | Description | Person | Index | No. | Number | Hours | Rand |  | Total | Total | Total
1 | Project Management |  | 2 | 1 | 237958 | 96 | 50400 | 1 | 50400 | 1 | 50401
2 | Platform Design |  | 39 | 2 | 303884 | 480 | 57600 | 1 | 57600 | 1 | 57601
3 | Explosion Proofing |  | 9 | 3 | 304032 | 192 | 37440 | 1 | 37440 | 1 | 37441
4 | Radio Communications |  | 27 | 4 | 250555 | 160 | 81600 | 1 | 81600 | 1 | 81601
5 | Camera Work |  | 28 | 5 | 235705 | 120 | 37800 | 1 | 37800 | 1 | 37801
|  |  | 1 | 5
|  |  | 1 | 5
|  |  | 1 | 5
|  |  | 1 | 5
|  |  | 1 | 5
|  |  | 1 | 5
|  |  | 1 | 5
|  |  | 1 | 5
|  |  | 1 | 5
|  |  | 1 | 5
|  |  | 1 | 5
|  |  | 1 | 5
|  |  | 1 | 5
|  |  | 1 | 5
|  |  | 1 | 5
|  |  | 1 | 5
|  |  | 1 | 5
|  |  | 1 | 5
|  |  | 1 | 5
|  |  | 1 | 5
|  |  | 1 | 5
|  |  | 1 | 5
|  |  | 1 | 5
|  |  | 1 | 5
|  |  | 1 | 5
|  |  | 1 | 5
|  |  | 1 | 5
|  |  | 1 | 5
|  |  | 1 | 5
|  |  | 1 | 5
|  |  | 1 | 5
|  |  | 1 | 5
|  |  | 1 | 5
|  |  | 1 | 5
|  |  | 1 | 5
|  |  | 1 | 5
|  |  | 1 | 5
|  |  | 1 | 5
|  |  | 1 | 5
|  |  | 1 | 5
Totals: | [5 empty] | 1048 |  |  | 264840 | 5 | 264845

## Labour Rates
Name, Pers No. , Labour Rate, OE2 | Bosscha P.A | 237958 | 525 | Mech
| Cele HM | 304177 | 105 | Micro
| Chen H. | 303243 | 195 | Micro
| Chiwewe T | 304605 | 285 | Mech
| Coetzee C.J | 205161 | 600 | Admin
| Conning M. | 302285 | 315 | Med
| Davies E.T.J | 302735 | 375 | Med
| Dickens J.S | 304032 | 195 | Mech
| du Toit JH | 305045 | 375 | Mech
| Fourie L.J | 302727 | 180 | Micro
| Govender U | 305809 | 240 | Micro
| Govindasamy K. | 303383 | 180 | Micro
| Green J | 303541 | 435 | Mech
| Joubert T | 305202 | 345 | Micro
| Kumar S. | 303758 | 180 | Micro
| Land K.J | 153437 | 420 | Micro
| Luvhengo T | 305497 | 90 | Mech
| Marais PA | 305193 | 180 | Med
| Mbanjwa M.B | 302198 | 255 | Micro
| Mbizeni A | 304548 | 120 | Mech
| Mjwana P | 305217 | 30 | Micro
| Mkhize A.T | 303844 | 105 | Admin
| Modungwa D.M | 302465 | 180 | Mech
| Mophuti L.A | 244657 | 270 | Admin
| Motloutsi MT | 305728 | 45 | Mech
| Naicker D.M | 250555 | 510 | Mech
| Naidoo T. | 235705 | 315 | Mech
| Ndlovu M. | 217638 | 150 | Mech
| Ngwenya SH | 305047 | 135 | Micro
| Nxumalo PZ | 305194 | 165 | Med
| Oosthuizen D | 304596 | 315 | Mech
| Potgieter S. | 302434 | 330 | Micro
| Purkis TL | 304468 | 60 | Med
| Rancati BS | 305091 | 195 | Mech
| Roux PW | 304667 | 435 | Med
| Smith S. | 303893 | 255 | Micro
| Stanton A. | 301437 | 360 | Med
| Steele AW | 303884 | 120 | Mech
| Swart J.H | 303896 | 210 | Mech
| Tapi M | 305805 | 45 | Mech
| Teleka S.R | 245324 | 225 | Mech
| Tlhoaele LT | 305142 | 30 | Mech
| Tyatyantsi A | 304406 | 150 | Mech
| van der Walt M | 304778 | 225 | Med
| Xungu S | 303875 | 120 | Mech
--- end of data --- end of data --- end of data --- end of data --- end of data --- end of data --- end of data --- end of data --- end of data --- end of data ---
Contribution Multiplier on Labour: | 1.6
Contribution Multiplier on Running: | 0

## Proposal-Export
Summary
|  |  | Planned | Planned | Contribution | Project
Workpackage | Work Package Description |  | Labour [R] | Running [R] | [R] | Total [R]
Phase 1 | Proof of Technical Concept |  | 264840 | 5 | 423744 | 688589
Phase 2 | Development and optimisation against the intended application |  | 529680 | 5 | 847488 | 1377173
Phase 3 | Prototype construction and laboratory testing |  | 264840 | 5 | 423744 | 688589
|  | Totals | 1059360 | 15 | 1694976 | 2754351
Financial Summary WP 1 |  | Staff Summary
|  |  | Total | Labour
Description | Value | Name | Hours | Cost
Total Hours: | 1048 | Bosscha P.A | 96 | 50400
Total Labour (R): | 264840 | Steele AW | 480 | 57600
Total Running (R): | 5 | Dickens J.S | 192 | 37440
Contribution (R): | 423744 | Naicker D.M | 160 | 81600
Grand Total (R): | 688589 | Naidoo T. | 120 | 37800
Financial Summary WP 2 |  | Staff Summary
|  |  | Total | Labour
Description | Value | Name | Hours | Cost
Total Hours: | 2096 | Bosscha P.A | 192 | 100800
Total Labour (R): | 529680 | Steele AW | 960 | 115200
Total Running (R): | 5 | Dickens J.S | 384 | 74880
Contribution (R): | 847488 | Naicker D.M | 320 | 163200
Grand Total (R): | 1377173 | Naidoo T. | 240 | 75600
Financial Summary WP 3 |  | Staff Summary
|  |  | Total | Labour
Description | Value | Name | Hours | Cost
Total Hours: | 1048 | Bosscha P.A | 96 | 50400
Total Labour (R): | 264840 | Steele AW | 480 | 57600
Total Running (R): | 5 | Dickens J.S | 192 | 37440
Contribution (R): | 423744 | Naicker D.M | 160 | 81600
Grand Total (R): | 688589 | Naidoo T. | 120 | 37800