## Summary
FINANCIAL SUMMARY
Project Title: | Chevron Aerial Drone
Project No : | -
Contract: | -
Manager | Angus Steele
Date: | 2015-02-10
Contribution: | 1.6
|  | Allocated |  |  | Planned |  |  |  | Ratios
|  | Revenue | Planned | Planned | Contrib | Project | Delta to | Running | Running | Contrib | Contrib
Workpackage | Work Package Description | ( R ) | Labour [R] | Running [R] | [R] | Total ( R ) | Allocated [R] | [1] | [2] | [3] | [4]
Phase 1 | Platform Development and Design Validation |  | 204600 | 40920 | 327360 | 572880 | -572880 |  | 7.1429 | 133.3333
Phase 2 | Investigation into novel control methods |  | 204600 | 40920 | 327360 | 572880 | -572880 |  | 7.1429 | 133.3333
Phase 3 | Application Specific investigations |  | 108600 | 21720 | 173760 | 304080 | -304080 |  | 7.1429 | 133.3333
| Totals | 0 | 517800 | 103560 | 828480 | 1449840 | -1449840 |  | 7.1429 | 133.3333
[1] Running Ratio = (Running / Revenue) *100
[2] Running Ratio = (Running / Project Total) *100
[3] Contribution Ratio = ( Contribution / ( HR+Running )) * 100
[4] Contribution Ratio = ( Contribution / Revenue) * 100

## WP_1
Project Title: | Chevron Aerial Drone
Project Number: | -
Contract: | -
Author: | Angus Steele
Date: | 2015-02-10
Financial Summary WP 1 |  | Staff Summary
|  |  | Person |  | Staff | Labour | Total | Labour
Description | Value | Name | Index |  | Number | Rate | Hours | Cost
Total Hours: | 1640 | Oosthuizen D | 32 |  | 304596 | 315 | 40 | 12600
Total Labour (R): | 204600 | Steele AW | 39 |  | 303884 | 120 | 1600 | 192000
Total Running (R): | 40920 | Dickens J.S | 9 |  | 304032 | 195 | 0 | 0
Contribution (R): | 327360 | Naicker D.M | 27 |  | 250555 | 510 | 0 | 0
Grand Total (R): | 572880 | Naidoo T. | 28 |  | 235705 | 315 | 0 | 0
1
1
1
1
1
1
1
Project Planning: | [7 empty] | Plan
|  |  | Person | Task | Staff | Labour | Labour | Running | Labour | Running | Task
Task No. | Description | Person | Index | No. | Number | Hours | Rand |  | Total | Total | Total
1 | Project Management |  | 32 | 1 | 304596 | 40 | 12600 | 1 | 12600 | 2520 | 15120
2 | Platform Design |  | 39 | 2 | 303884 | 1600 | 192000 | 1 | 192000 | 38400 | 230400
|  |  | 9 | 2
|  |  | 27 | 2
|  |  | 28 | 2
|  |  | 1 | 2
|  |  | 1 | 2
|  |  | 1 | 2
|  |  | 1 | 2
|  |  | 1 | 2
|  |  | 1 | 2
|  |  | 1 | 2
|  |  | 1 | 2
|  |  | 1 | 2
|  |  | 1 | 2
|  |  | 1 | 2
|  |  | 1 | 2
|  |  | 1 | 2
|  |  | 1 | 2
|  |  | 1 | 2
|  |  | 1 | 2
|  |  | 1 | 2
|  |  | 1 | 2
|  |  | 1 | 2
|  |  | 1 | 2
|  |  | 1 | 2
|  |  | 1 | 2
|  |  | 1 | 2
|  |  | 1 | 2
|  |  | 1 | 2
|  |  | 1 | 2
|  |  | 1 | 2
|  |  | 1 | 2
|  |  | 1 | 2
|  |  | 1 | 2
|  |  | 1 | 2
|  |  | 1 | 2
|  |  | 1 | 2
|  |  | 1 | 2
|  |  | 1 | 2
|  |  | 1 | 2
|  |  | 1 | 2
|  |  | 1 | 2
|  |  | 1 | 2
|  |  | 1 | 2
Totals: | [5 empty] | 1640 |  |  | 204600 | 40920 | 245520
Note on I39: User @: Fortran Compiler

## WP_2
Project Title: | Chevron Aerial Drone
Project Number: | -
Contract: | -
Author: | Angus Steele
Date: | 2015-02-10
Financial Summary WP2 |  | Staff Summary
|  |  | Person |  | Staff | Labour | Total | Labour
Description | Value | Name | Index |  | Number | Rate | Hours | Cost
Total Hours: | 1640 | Oosthuizen D | 32 |  | 304596 | 315 | 40 | 12600
Total Labour (R): | 204600 | Steele AW | 39 |  | 303884 | 120 | 1600 | 192000
Total Running (R): | 40920 | Dickens J.S | 9 |  | 304032 | 195 | 0 | 0
Contribution (R): | 327360 | Naicker D.M | 27 |  | 250555 | 510 | 0 | 0
Grand Total (R): | 572880 | Naidoo T. | 28 |  | 235705 | 315 | 0 | 0
1
1
1
1
1
1
1
Project Planning: | [7 empty] | Plan
|  |  | Person | Task | Staff | Labour | Labour | Running | Labour | Running | Task
Task No. | Description | Person | Index | No. | Number | Hours | Rand |  | Total | Total | Total
1 | Project Management |  | 32 | 1 | 304596 | 40 | 12600 | 1 | 12600 | 2520 | 15120
2 | Platform Design |  | 39 | 2 | 303884 | 1600 | 192000 | 1 | 192000 | 38400 | 230400
|  |  | 9 | 2
|  |  | 27 | 2
|  |  | 28 | 2
|  |  | 1 | 2
|  |  | 1 | 2
|  |  | 1 | 2
|  |  | 1 | 2
|  |  | 1 | 2
|  |  | 1 | 2
|  |  | 1 | 2
|  |  | 1 | 2
|  |  | 1 | 2
|  |  | 1 | 2
|  |  | 1 | 2
|  |  | 1 | 2
|  |  | 1 | 2
|  |  | 1 | 2
|  |  | 1 | 2
|  |  | 1 | 2
|  |  | 1 | 2
|  |  | 1 | 2
|  |  | 1 | 2
|  |  | 1 | 2
|  |  | 1 | 2
|  |  | 1 | 2
|  |  | 1 | 2
|  |  | 1 | 2
|  |  | 1 | 2
|  |  | 1 | 2
|  |  | 1 | 2
|  |  | 1 | 2
|  |  | 1 | 2
|  |  | 1 | 2
|  |  | 1 | 2
|  |  | 1 | 2
|  |  | 1 | 2
|  |  | 1 | 2
|  |  | 1 | 2
|  |  | 1 | 2
|  |  | 1 | 2
|  |  | 1 | 2
|  |  | 1 | 2
|  |  | 1 | 2
Totals: | [5 empty] | 1640 |  |  | 204600 | 40920 | 245520

## WP_3
Project Title: | Chevron Aerial Drone
Project Number: | -
Contract: | -
Author: | Angus Steele
Date: | 2015-02-10
Financial Summary WP3 |  | Staff Summary
|  |  | Person |  | Staff | Labour | Total | Labour
Description | Value | Name | Index |  | Number | Rate | Hours | Cost
Total Hours: | 840 | Oosthuizen D | 32 |  | 304596 | 315 | 40 | 12600
Total Labour (R): | 108600 | Steele AW | 39 |  | 303884 | 120 | 800 | 96000
Total Running (R): | 21720 | Dickens J.S | 9 |  | 304032 | 195 | 0 | 0
Contribution (R): | 173760 | Naicker D.M | 27 |  | 250555 | 510 | 0 | 0
Grand Total (R): | 304080 | Naidoo T. | 28 |  | 235705 | 315 | 0 | 0
1
1
1
1
1
1
1
Project Planning: | [7 empty] | Plan
|  |  | Person | Task | Staff | Labour | Labour | Running | Labour | Running | Task
Task No. | Description | Person | Index | No. | Number | Hours | Rand |  | Total | Total | Total
1 | Project Management |  | 32 | 1 | 304596 | 40 | 12600 | 1 | 12600 | 2520 | 15120
2 | Platform Design |  | 39 | 2 | 303884 | 800 | 96000 | 1 | 96000 | 19200 | 115200
3 |  |  | 9 | 3 |  |  |  |  | 0 | 0 | 0
|  |  | 27 | 3
|  |  | 28 | 3
|  |  | 1 | 3
|  |  | 1 | 3
|  |  | 1 | 3
|  |  | 1 | 3
|  |  | 1 | 3
|  |  | 1 | 3
|  |  | 1 | 3
|  |  | 1 | 3
|  |  | 1 | 3
|  |  | 1 | 3
|  |  | 1 | 3
|  |  | 1 | 3
|  |  | 1 | 3
|  |  | 1 | 3
|  |  | 1 | 3
|  |  | 1 | 3
|  |  | 1 | 3
|  |  | 1 | 3
|  |  | 1 | 3
|  |  | 1 | 3
|  |  | 1 | 3
|  |  | 1 | 3
|  |  | 1 | 3
|  |  | 1 | 3
|  |  | 1 | 3
|  |  | 1 | 3
|  |  | 1 | 3
|  |  | 1 | 3
|  |  | 1 | 3
|  |  | 1 | 3
|  |  | 1 | 3
|  |  | 1 | 3
|  |  | 1 | 3
|  |  | 1 | 3
|  |  | 1 | 3
|  |  | 1 | 3
|  |  | 1 | 3
|  |  | 1 | 3
|  |  | 1 | 3
|  |  | 1 | 3
Totals: | [5 empty] | 840 |  |  | 108600 | 21720 | 130320

## Labour Rates
Name, Pers No. , Labour Rate, OE2 | Bosscha P.A | 237958 | 525 | Mech
| Cele HM | 304177 | 105 | Micro
| Chen H. | 303243 | 195 | Micro
| Chiwewe T | 304605 | 285 | Mech
| Coetzee C.J | 205161 | 600 | Admin
| Conning M. | 302285 | 315 | Med
| Davies E.T.J | 302735 | 375 | Med
| Dickens J.S | 304032 | 195 | Mech
| du Toit JH | 305045 | 375 | Mech
| Fourie L.J | 302727 | 180 | Micro
| Govender U | 305809 | 240 | Micro
| Govindasamy K. | 303383 | 180 | Micro
| Green J | 303541 | 435 | Mech
| Joubert T | 305202 | 345 | Micro
| Kumar S. | 303758 | 180 | Micro
| Land K.J | 153437 | 420 | Micro
| Luvhengo T | 305497 | 90 | Mech
| Marais PA | 305193 | 180 | Med
| Mbanjwa M.B | 302198 | 255 | Micro
| Mbizeni A | 304548 | 120 | Mech
| Mjwana P | 305217 | 30 | Micro
| Mkhize A.T | 303844 | 105 | Admin
| Modungwa D.M | 302465 | 180 | Mech
| Mophuti L.A | 244657 | 270 | Admin
| Motloutsi MT | 305728 | 45 | Mech
| Naicker D.M | 250555 | 510 | Mech
| Naidoo T. | 235705 | 315 | Mech
| Ndlovu M. | 217638 | 150 | Mech
| Ngwenya SH | 305047 | 135 | Micro
| Nxumalo PZ | 305194 | 165 | Med
| Oosthuizen D | 304596 | 315 | Mech
| Potgieter S. | 302434 | 330 | Micro
| Purkis TL | 304468 | 60 | Med
| Rancati BS | 305091 | 195 | Mech
| Roux PW | 304667 | 435 | Med
| Smith S. | 303893 | 255 | Micro
| Stanton A. | 301437 | 360 | Med
| Steele AW | 303884 | 120 | Mech
| Swart J.H | 303896 | 210 | Mech
| Tapi M | 305805 | 45 | Mech
| Teleka S.R | 245324 | 225 | Mech
| Tlhoaele LT | 305142 | 30 | Mech
| Tyatyantsi A | 304406 | 150 | Mech
| van der Walt M | 304778 | 225 | Med
| Xungu S | 303875 | 120 | Mech
--- end of data --- end of data --- end of data --- end of data --- end of data --- end of data --- end of data --- end of data --- end of data --- end of data ---
Contribution Multiplier on Labour: | 1.6
Contribution Multiplier on Running: | 0

## Proposal-Export
Summary
|  |  | Planned | Planned | Contribution | Project
Workpackage | Work Package Description |  | Labour [R] | Running [R] | [R] | Total [R]
Phase 1 | Platform Development and Design Validation |  | 204600 | 40920 | 327360 | 572880
Phase 2 | Investigation into novel control methods |  | 204600 | 40920 | 327360 | 572880
Phase 3 | Application Specific investigations |  | 108600 | 21720 | 173760 | 304080
|  | Totals | 517800 | 103560 | 828480 | 1449840
Financial Summary WP 1 |  | Staff Summary
|  |  | Total | Labour
Description | Value | Name | Hours | Cost
Total Hours: | 1640 | Oosthuizen D | 40 | 12600
Total Labour (R): | 204600 | Steele AW | 1600 | 192000
Total Running (R): | 40920 | Dickens J.S | 0 | 0
Contribution (R): | 327360 | Naicker D.M | 0 | 0
Grand Total (R): | 572880 | Naidoo T. | 0 | 0
Financial Summary WP 2 |  | Staff Summary
|  |  | Total | Labour
Description | Value | Name | Hours | Cost
Total Hours: | 1640 | Oosthuizen D | 40 | 12600
Total Labour (R): | 204600 | Steele AW | 1600 | 192000
Total Running (R): | 40920 | Dickens J.S | 0 | 0
Contribution (R): | 327360 | Naicker D.M | 0 | 0
Grand Total (R): | 572880 | Naidoo T. | 0 | 0
Financial Summary WP 3 |  | Staff Summary
|  |  | Total | Labour
Description | Value | Name | Hours | Cost
Total Hours: | 840 | Oosthuizen D | 40 | 12600
Total Labour (R): | 108600 | Steele AW | 800 | 96000
Total Running (R): | 21720 | Dickens J.S | 0 | 0
Contribution (R): | 173760 | Naicker D.M | 0 | 0
Grand Total (R): | 304080 | Naidoo T. | 0 | 0